# DB Migration — Wave 4 cutover plan v2

Owner: Priya Raman (priya.sre), cutover operations    Status: Approved for rehearsal    Ticket: DBMIG-12

# 1. What changed since v1

The wave 4 ledger cutover (DBMIG-12) is rescheduled to Saturday 14 November 2026, 22:00 SGT. Version 1 of this plan said 24 October 2026.

Why: the ledger-shard-3 copy job was paused at batch 1,812 after replication lag passed 40 seconds, and the refund idempotency fix (DBMIG-14) has to land before the final backfill. The overall approach is unchanged; see the DB Migration Plan: https://companya.atlassian.net/wiki/spaces/payment-gateway/pages/cf-1001

# 2. Cutover window

Start: Saturday 14 November 2026, 22:00 SGT (payments traffic lowest).

Write freeze: 22:00 to 23:30 SGT; card authorisations keep flowing through the dual-write shim.

Go / no-go call: 21:30 SGT, chaired by Nina Kowalski.

Fallback date if the call says no-go: Saturday 21 November 2026, same times.

# 3. Steps

| Step | Time (SGT) | Action | Owner |
| --- | --- | --- | --- |
| 1 | 21:30 | Go / no-go call; confirm replica lag under 5 s on all four ledger shards | nina.k |
| 2 | 22:00 | Freeze ledger writes on the Postgres 11 cluster; dual-write shim to drain mode | jdoe |
| 3 | 22:10 | Final backfill delta for ledger shards 1-4; verify row counts and checksums | priya.sre |
| 4 | 22:45 | Flip the ledger read path to the managed Postgres 16 cluster | priya.sre |
| 5 | 23:00 | Smoke tests: authorisation, refund, settlement file dry run | wei.l |
| 6 | 23:30 | Lift the write freeze; old cluster stays read-only for 7 days | priya.sre |

# 4. Rollback

Until step 6, the Postgres 11 cluster remains the source of truth. Rollback is a flag flip of the dual-write shim back to primary-old, then a replay of the delta captured after step 2. Decision owner: Priya Raman.

# 5. Sign-off

Nina Kowalski (plan owner), Priya Raman (cutover operations), Jordan Doe (dual-write shim), Yuki Sato (data platform).

Company A internal - synthetic demonstration data, invented for Walnut DataBridge.